## ProjectMonitoring
Programme | Batch (Start Yr - End Yr) | 2020-2024 | Project: | Unveiling Clickbait and Unmasking Fake News: A Multimodal Analysis Leveraging User Influence on Twitter
B.Tech CSE | Group | 3 | Names: | Anurag (13000120103), Abhinab Paul (13000120107), Uttkarsh Ranjan (13000120109), Priyasu Guin (13000120117)
Attendance (Insert below names)
Date | Project discussions |  |  |  | Semester | Deliverable | Issues | Guide's remark | Anurag (13000120103) | Abhinab Paul (13000120107) | Uttkarsh Ranjan (13000120109) | Priyasu Guin (13000120117)
26/08/23 | Exploring of project domains, sorting on potential project topics |  |  |  | 7 | Potential project topics with some working approaches for each | - | Team needs to fixate on a topic of choice so the next batch of workings can start | Present | Present | Present | Present
2023-09-09 | Different approaches to start with Fake Content Detection on social media, research papers, finding datasets |  |  |  | 7 | Datasets for real and fake news, futher detailed workflow | Finding a dataset that consists of all the attributes that we needed was difficult | Study different research papers online to get familiar with the field of work we're doing | Present | Present | Present | Present
23/09/23 | Pros and cons of each dataset we encountered, fixating on which one we'll proceed with, corrections in workflow |  |  |  | 7 | Changed Workflows, finalized dataset to start with further processing | Different social media platforms will have different set of features, we needed to fixate on one for the time being | - | Present | Present | Present | Present
30/09/23 | Agreed upon twitter as the platform to be targetted, and finalizing the TweetaVerse Dataset for the same. Finalized the current worlkflows and discussed on further improvements like phishing links detection |  |  |  | 7 | Complete dataset for tweets classification, potential datasets for phishing links classifier | Lack of sufficient features for our needing, thus we'll have to extract features of our own | Need to use our own parameters for detecting user influence | Present | Present | Absent | Absent
14/10/23 | Finishing up on Mid term Deliverables, Finalizing the URL Guardian dataset, changes to workflows |  |  |  | 7 | Credible sources for the datasets, research papers for exploring semantics classification | Human sentiment analysis is still an area that is under reasearch and hence is very difficult to work with | Credibility of the datasets curated must be ensured | Present | Present | Present | Present
27/10/23 | Veryfying results of Tweets Classifier, looking for better approaches, looking at results for links classifier, apporaches for semantics classifier |  |  |  | 7 | Documentations, properly labelled datasets for final submissions | - | Need to go through research papers for understanding sarcasm and other human sentiments | Absent | Present | Present | Present
2023-04-11 | Final review of Tweets and Links Classifier, exploring papers for semantics detection |  |  |  | 7 | Semantics Classifier | Lack of adequate datasets | - | Present | Present | Present | Present
2023-11-11 | Changes in PRD, classifier results review, minor fixes |  |  |  | 7 | Final updated documnets for submission | - | No mistakes/descripancies must be found across any deliverable | Present | Absent | Present | Present
17/11/23 | Final review of PRD and other deliverables |  |  |  | 7 | - | - | - | Present | Present | Present | Present
2024-02-02 | Taking up from where we left, new approaches for semantics detection, exploration for the multimedia datasets |  |  |  | 8 | Image datasets, semantics classifier datasets | Difficult to find fake images dataset with relevant features for Twitter, same goes for the semantics as well | Curate the dataset if possible, else will have to go through non traditional ways | Present | Absent | Present | Absent
17/02/24 | Working on the semantics classifer without a dataset, rather reyling on intuitive thinking gathered from multiple research papers, continuing exploring more image datasets and avoiding having to curate one |  |  |  | 8 | Final image dataset, workings for the semantics classifier | Curating a dataset on our own was very difficult, that too one which includes images | - | Present | Present | Present | Present
2024-02-03 | Review + updates on semantics classification, documentations, finalizing the image dataset, various models for image classifier |  |  |  | 8 | Trained models for image classifier | Training could only be done a couple of times, since CNN models take a long time to train | Image dataset must have sufficient no. of samples for the models to reach satisfactory results. Moreover, the dataset must be from a credible source | Present | Present | Absent | Present
16/03/24 | Finalizing the semantics classifier, comparing results for image classifier |  |  |  | 8 | Image classifier | - | Try using different variations of CNN models | Present | Present | Present | Present
13/04/24 | Finalzing the image classifier and working on workflows for the project |  |  |  | 8 | Final version of the classifiers for the project | - | - | Absent | Present | Present | Present
27/04/24 | Final review of all the classifiers from current and last semester |  |  |  | 8 | Updated documentations | - | Incorporate all the details from both semesters into the documentations | Present | Present | Present | Present
17/05/24 | Changes in prd, minor fixes in documentations, review of workings |  |  |  | 8 | - | - | Documentations must be completed well before the deadline | Present | Absent | Present | Absent
25/05/24 | Final documentations and project review |  |  |  | 8 | - | - | - | Present | Present | Present | Present
Total | [8 empty] | 88.24% | 82.35% | 88.24% | 82.35%
Overall | [8 empty] | 88.24% | 82.35% | 88.24% | 82.35%
Guide's signature:
(When maintained on hard-copy)

## Questions
Area | Question | Raised By | Status (Open / Closed) | Response | Response By
Project scope | How would be able to address different input formats on different social media platforms | PD Ma'am | Closed | We can limit ourselves to working with a single platform for the time being and build models that'll be trained on the actual data rather than the type of platform | Priyasu
Datasets | Where would be get such a dataset which is large enough to train our model with satisfactory results? | Everyone | Closed | Exploration on the internet led us to such a dataset, but we still had to perform computations on that | Anurag, Priyasu, Abhinab
Credebility | How do we know that the source we're using are credible? | PD Ma'am | Closed | Research papers upon which the works were based | Priyasu
Uniqueness | How will our project stand out? | Everyone | Closed | Working with user influence, multimodality, human sentiments | PD Ma'am
User Influence | How to calculate them? | PD Ma'am | Closed | Bot score, cred score, exclusivity | Uttkarsh
Workflow | How would be go about working on this? | Everyone | Closed | Detailed workflows for each classifier which were refined upon iteratively | Anurag
Hyperparameters | How to choose the right values? | Everyone | Closed | Analyzing statistics of our dataset | Abhinab
Documentations | What all things need to be included, in what depth, in which manner? | Everyone | Closed | Templates | PD Ma'am
Pesentation | Contents of the PPT? | Uttkarsh | Closed | Templates | PD Ma'am
Multimodality | How to focus on the multimedia front? | PD Ma'am | Closed | Currently will focus on images | Priyasu
Sematics Classifier | How to proceed in this regard? | PD Ma'am | Closed | Will rely on intuitive logic rather than datasets | Anurag, Uttkarsh
Final documentations | Which content to include from last semester, new contents, other things? | Everyone | Closed | Templates | PD Ma'am